## Jira Backlog
Epic | User Story | Description | Story Points | Branch Name | Priority | Status
Project Setup | Initialize Flask Project | Set up Flask project structure and virtual environment | 3 | feature/project-setup | High | To Do
Project Setup | Configure Dependencies | Add requirements.txt with Flask, Transformers, Torch | 2 | feature/dependencies-config | High | To Do
NLP Integration | Load Translation Model | Integrate Helsinki-NLP/opus-mt-en-hi model using Hugging Face | 5 | feature/model-integration | High | To Do
NLP Integration | Create Translation Service | Develop Python service to handle text translation logic | 5 | feature/translation-service | High | To Do
API Development | Create /translate API | Develop REST endpoint to accept text and return translation | 3 | feature/translate-api | High | To Do
Frontend UI | Build Input Interface | Create HTML page with input textbox and translate button | 3 | feature/ui-input | Medium | To Do
Frontend UI | Display Translation Result | Show translated Hindi output dynamically | 2 | feature/ui-output | Medium | To Do
UX Improvements | Add Loading Indicator | Show loader while translation is processing | 1 | feature/loading-indicator | Low | To Do
Error Handling | Input Validation | Prevent empty submissions and show error messages | 2 | feature/input-validation | Medium | To Do
Deployment | Prepare Render Deployment | Configure render.yaml and start command | 3 | feature/render-deployment | High | To Do
Deployment | Environment Configuration | Set environment variables and port configuration | 2 | feature/env-config | Medium | To Do
Testing | API Testing | Test translation endpoint with multiple inputs | 3 | feature/api-testing | Medium | To Do
Testing | UI Testing | Cross-browser testing and responsiveness checks | 2 | feature/ui-testing | Low | To Do
Documentation | Create README | Add setup, usage, and deployment instructions | 2 | feature/readme-docs | Low | To Do